## Project Overview
Northwind Technologies – CRM Implementation
Business analysis case study. Northwind Technologies and all names, dates and estimates are fictitious.
1. Business problem
Current situation | Sales Representatives keep customer contacts in separate spreadsheets and inboxes. This causes duplicate and out-of-date records, no clear view of the sales pipeline, and missed meetings and follow-ups. Sales Managers have no easy way to report on team performance.
Proposed solution | A central CRM system with contact management, sales opportunity tracking, reporting dashboards, and Outlook email and calendar integration with automated reminders.
2. Objectives and success measures (illustrative targets)
Accurate contact data | One central contact list; duplicate contacts below 2% three months after go-live.
Pipeline visibility | All open sales opportunities tracked in the CRM by sales stage.
Faster reporting | Sales Managers can produce a weekly sales report in under 10 minutes.
Fewer missed follow-ups | Automatic reminders for all booked meetings and follow-up tasks that are due.
3. Scope
In scope | Contact management (including import and export); sales opportunity tracking; reporting and analytics dashboards; Outlook email and calendar integration with automated reminders; performance, security, privacy and audit NFRs.
Out of scope (assumed) | Marketing campaign automation; customer self-service portal; native mobile app; integration with finance or invoicing systems; migration of historical email archives.
4. Delivery approach
Method | Scrum, 2-week sprints. 8 sprints (80 working days) plus 1 day for project closure = 81 working days.
Planned start date | 2026-10-12 | Linked to the Gantt Chart (cell E4) – change the date there to move the whole plan.
5. Stakeholders and project team
Name | Role | Responsibility
Emily Johnson | Project Sponsor (assumed) | Approves budget and scope; signs off project completion (milestone M5).
Michael Lee | Head of Sales / Business Owner (assumed) | Represents sales team needs; signs off project completion (milestone M5).
Sarah | Product Owner | Owns and prioritises the backlog; accepts stories; owns milestones M1–M4.
David | Scrum Master | Runs Scrum events and removes blockers; leads project closure.
Tom | Business Analyst | Elicits and refines requirements, stories and acceptance criteria; maintains traceability.
Rachel | UX/UI Designer | Designs pages and user flows.
Lisa | Frontend Developer | Builds user-facing pages.
Mark | Backend Developer | Builds database, APIs and integrations.
Alex | QA / Tester | Writes and runs test cases from acceptance criteria; performance testing.
Sales Representatives | End users | Manage contacts and opportunities day to day.
Sales Managers | End users | Use reports and dashboards to track team performance.
6. Key assumptions
• | Northwind uses Microsoft Outlook for email and calendar.
• | The Scrum team works full time on this project.
• | Durations are in working days (Mon–Fri); NZ public holidays and the Christmas break are not included.
• | Priorities, story points and success targets are illustrative for this exercise.
7. How to read this workbook
Requirements | Functional requirements (REQ) and non-functional requirements (NFR).
EPICS | Four epics (EP-01 to EP-04), one per feature, with high-level acceptance criteria.
User Stories | EP-01 Contact Management split into 11 user stories with acceptance criteria, priority and story points.
Roadmap | High-level 17-week plan by phase.
Gantt Chart | Detailed schedule with owners, dependencies and milestones (formula-driven dates).
Traceability Matrix | Links each requirement to epics, user stories, tasks and test cases.
Risk Log | Key delivery risks with rating, mitigation and owner.

## Requirements
Feature | Req ID | Requirements
Contact Management | REQ-01 | Enable sales representatives to list, view, add, edit, and delete customer contacts. Contact details must include customer name, company name, email, phone, additional details.
| REQ-02 | Allow users to import and export contact lists.
Sales Opportunity Tracking | REQ-03 | Implement functionality for users to create and update sales opportunities.
| REQ-04 | Provide a visual sales pipeline to track opportunities through different stages of the sales cycle.
Reporting and Analytics | REQ-05 | Generate reports on sales performance and customer interactions.
| REQ-06 | Provide dashboard analytics to visualize sales data.
Integration and Automation | REQ-07 | Integrate the CRM with email and calendar systems.
| REQ-08 | Automate reminders and follow-up tasks for sales representatives.
System Performance NFRs | NFR-01 | The system should be able to handle at least 500 concurrent users without any degradation in performance.
| NFR-02 | Page load times for any CRM feature must not exceed 3 seconds under normal network conditions.
Security & Privacy NFRs | NFR-03 | Role-based access: users can only edit and delete records they are allowed to. Sales Representatives can delete only contacts and opportunities they own; Sales Managers can delete any record and view team-wide reports.
| NFR-04 | Privacy: customer personal information must be handled in line with the NZ Privacy Act 2020. Data is encrypted in transit and at rest, access is limited to authorised users, and a contact's details can be exported or removed on request.
| NFR-05 | Audit trail: the system records who created, changed or deleted each contact and opportunity, and when. Audit records are kept for at least 2 years.

## EPICS
Feature | Epic ID | EPIC
Contact Management | EP-01 | As a Sales Representative, I want to manage all customer contacts in one central place, so that customer information is accurate, up to date and free of duplicates. Acceptance criteria: EP-01-01: Sales Representatives can list, view, add, edit and delete customer contacts (customer name, company name, email, phone and additional details). EP-01-02: Users can import and export contact lists.
Sales Opportunity Tracking | EP-02 | As a Sales Representative, I want to create and update sales opportunities and see them by sales stage, so that I can prioritise leads and close deals faster. Acceptance criteria: EP-02-01: Users can create a sales opportunity linked to a contact and update its stage, value and expected close date. EP-02-02: A dashboard shows all opportunities grouped by stage of the sales cycle (e.g. Lead, Qualified, Proposal, Won, Lost).
Reporting and Analytics | EP-03 | As a Sales Manager, I want to view dashboard analytics and sales reports, so that I can understand team performance and customer interactions and make better decisions. Acceptance criteria: EP-03-01: Sales Managers can view dashboard analytics that show team performance and customer interactions. EP-03-02: Sales Managers can generate and download sales reports.
Integration and Automation | EP-04 | As a Sales Representative, I want the CRM to connect with my Outlook email and calendar and send me automatic reminders, so that I never miss a meeting or a customer follow-up. Acceptance criteria: EP-04-01: The CRM syncs with Outlook email and calendar; meetings booked in the CRM appear in Outlook, and customer emails are logged against the contact. EP-04-02: The system sends automatic reminders for upcoming meetings and follow-up tasks that are due.

## User Stories
ID | User Story Title | User Story Description | Relates to Epic | AC ID | Acceptance Criteria | Priority (MoSCoW) | Story Points
US-01 | List Customer Contacts | As a Sales Representative, I want to see a list of all customer contacts, so that I can quickly find the customer I need to contact. | EP-01 | US-01-01 | The list shows customer name, company name, email and phone for each contact. | Must | 5
|  |  |  | US-01-02 | The list shows 25 contacts per page, sorted A–Z by customer name by default; the user can sort by any column.
|  |  |  | US-01-03 | If there are no contacts, the message "No contacts found. Add your first contact." is shown with an Add Contact button.
|  |  |  | US-01-04 | If the list cannot load (system error), an error message with a Retry button is shown and no partial data is displayed.
US-02 | View Contact Details | As a Sales Representative, I want to open a contact and see all of its details, so that I have the full customer information before I call or email them. | EP-01 | US-02-01 | Clicking a contact in the list opens a detail page showing customer name, company name, email, phone and additional details. | Must | 3
|  |  |  | US-02-02 | The detail page shows the date the contact was created and when (and by whom) it was last updated.
|  |  |  | US-02-03 | If the contact no longer exists (e.g. deleted by another user), the message "This contact is no longer available" is shown and the user returns to the list.
US-03 | Add New Contact | As a Sales Representative, I want to add a new customer contact, so that every new customer is recorded in one central place. | EP-01 | US-03-01 | An Add Contact form has fields for customer name, company name, email, phone and additional details; customer name and email are mandatory. | Must | 3
|  |  |  | US-03-02 | Given the Add Contact form has valid details, When the user clicks Save, Then the contact is stored, appears in the contact list, and the message "Contact added" is shown.
|  |  |  | US-03-03 | When the user clicks Cancel, the form closes and nothing is saved.
US-04 | Validate Contact Details | As a Sales Representative, I want the system to check contact details when I add or edit a contact, so that records stay accurate and duplicates are avoided. | EP-01 | US-04-01 | If a mandatory field is empty, the contact is not saved and the field is highlighted with the message "This field is required". | Must | 3
|  |  |  | US-04-02 | If the email format is invalid or the phone number contains letters, an error message is shown and the contact is not saved.
|  |  |  | US-04-03 | Given a contact with the same email already exists, When the user tries to save a contact with that email, Then the warning "A contact with this email already exists" is shown with a link to the existing contact, and no duplicate is created.
US-05 | Edit Contact | As a Sales Representative, I want to edit a contact's details, so that customer information stays up to date. | EP-01 | US-05-01 | The user can click Edit on the contact detail page, change any field and save the changes. | Must | 3
|  |  |  | US-05-02 | The same validation rules as US-04 apply when editing.
|  |  |  | US-05-03 | After saving, the updated details show in the list and detail page, and the "last updated" date and user are refreshed.
|  |  |  | US-05-04 | If saving fails (system error), the user's changes are kept on screen, an error message is shown and the user can try again.
US-06 | Delete Contact | As a Sales Representative, I want to delete a contact I no longer need, so that the contact list stays clean and relevant. | EP-01 | US-06-01 | When the user clicks Delete, a confirmation message "Are you sure you want to delete this contact?" is shown. | Should | 2
|  |  |  | US-06-02 | If the user confirms, the contact is removed from the list and the message "Contact deleted" is shown.
|  |  |  | US-06-03 | If the user cancels, the contact is not deleted.
|  |  |  | US-06-04 | Given the contact is linked to an open sales opportunity, When the user clicks Delete, Then a warning is shown and the user must confirm before the contact is deleted.
US-07 | Search and Filter Contacts | As a Sales Representative, I want to search and filter contacts, so that I can find a customer quickly in a large list. | EP-01 | US-07-01 | The user can search by customer name, company name or email; results update after at least 2 characters are typed. | Should | 3
|  |  |  | US-07-02 | The user can filter the list by company name.
|  |  |  | US-07-03 | If no contacts match, the message "No matching contacts found" is shown.
US-08 | Import Contacts | As a Sales Representative, I want to import contacts from a CSV or Excel file, so that I can move existing spreadsheet data into the CRM without retyping it. | EP-01 | US-08-01 | The user can download an import template and upload a .csv or .xlsx file up to 5 MB. | Should | 5
|  |  |  | US-08-02 | Before importing, the system shows a preview of the data and lets the user match file columns to contact fields.
|  |  |  | US-08-03 | After import, a summary shows how many contacts were imported, skipped and failed.
US-09 | Handle Import Errors | As a Sales Representative, I want the system to tell me which rows could not be imported and why, so that I can fix my file and avoid bad or duplicate data. | EP-01 | US-09-01 | Unsupported file types or files over 5 MB are rejected with a clear error message. | Should | 3
|  |  |  | US-09-02 | Given the import file has rows with missing mandatory fields or an invalid email, When the user imports the file, Then those rows are skipped and listed in an error report the user can download.
|  |  |  | US-09-03 | Rows whose email matches an existing contact are flagged as duplicates, and the user chooses to skip or update them.
US-10 | Export Contacts | As a Sales Representative, I want to export contacts to a CSV or Excel file, so that I can share them or use them in other tools. | EP-01 | US-10-01 | The user can export all contacts, or only the current search/filter results, to .csv or .xlsx. | Should | 2
|  |  |  | US-10-02 | The exported file includes column headers and all contact fields (customer name, company name, email, phone, additional details).
|  |  |  | US-10-03 | If there are no contacts to export, the Export button is disabled.
US-11 | Contact Module Performance | As a Sales Representative, I want contact pages to load quickly even when the whole team is using the CRM, so that I can serve customers without delays. | EP-01 | US-11-01 | Load testing shows the contact module supports at least 500 concurrent users with no drop in performance. | Must | 3
|  |  |  | US-11-02 | The contact list, detail, add and edit pages load in 3 seconds or less under normal network conditions.
Notes: Priority uses MoSCoW (Must / Should / Could / Won't). Story points use the Fibonacci scale (1, 2, 3, 5, 8) and are illustrative estimates for this exercise, sized to match the Gantt chart durations. Acceptance criteria use two styles: rule-based statements and Given / When / Then (see US-03-02, US-04-03, US-06-04, US-09-02).

## Roadmap
ID | Phase/Key Milestone | Duration | Week _01 | Week _02 | Week _03 | Week _04 | Week _05 | Week _06 | Week _07 | Week _08 | Week _09 | Week _10 | Week _11 | Week _12 | Week _13 | Week _14 | Week _15 | Week _16 | Week _17
1 | Contact Management: Sales representatives can manage customer contacts easily. | 20 days
2 | Sales Opportunity Tracking: Users can track sales opportunities and update their status. | 10 days
3 | Reporting and Analytics: Sales managers can gain insights into team performance and customer interactions. | 30 days
4 | Integration and Automation: CRM integrated with Outlook email & calendar, sales staff receive automated reminders about meetings and tasks | 20 days
5 | Project Closure | 1 day
| Total | 81 days

## Gantt Chart
Calendar date of each day column → | time axis 2026-10-12 to 2027-02-14
| Project : Northwind Technologies CRM Implementation | Resource | Duration | Start | End | 2026-10-12: Sprint 1; 2026-10-26: Sprint 2; 2026-11-09: Sprint 3; 2026-11-23: Sprint 4; 2026-12-07: Sprint 5; 2026-12-21: Sprint 6; 2027-01-04: Sprint 7; 2027-01-18: Sprint 8; 2027-02-01: Sprint 9
Ref | Phase, User Story/Task | Role or person | Days | Date | Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| Project start date (Monday) – edit cell E4 to move the whole plan → |  |  | 2026-10-12
1.0 | Phase 1: Contact Management (Epic EP-01) | Scrum Team | 20 | 2026-10-12 | 2026-11-06
1.1 | US-01 List Customer Contacts | Scrum Team | 7 | 2026-10-12 | 2026-10-20
TASK-01 | Refine story & acceptance criteria with Product Owner | Tom (BA) | 1 | 2026-10-12 | 2026-10-12
TASK-02 | "Contact list" page design (after TASK-01) | Rachel (UX/UI) | 1 | 2026-10-13 | 2026-10-13
TASK-03 | Contacts database table & list API – paging, sorting (after TASK-01) | Mark (Backend) | 2 | 2026-10-13 | 2026-10-14
TASK-04 | Write test cases from acceptance criteria (after TASK-01) | Alex (QA) | 1 | 2026-10-13 | 2026-10-13
TASK-05 | Build contact list page – table, paging, empty & error states (after TASK-02, TASK-03) | Lisa (Frontend) | 2 | 2026-10-15 | 2026-10-16
TASK-06 | Test and fix bugs (after TASK-05) | Alex (QA), Lisa, Mark | 1 | 2026-10-19 | 2026-10-19
TASK-07 | Story review & acceptance sign-off (after TASK-06) | Tom (BA), Sarah (PO) | 1 | 2026-10-20 | 2026-10-20
1.2 | US-02 View Contact Details (after TASK-05) | Scrum Team | 3 | 2026-10-19 | 2026-10-21
1.3 | US-03 Add New Contact (after US-01) | Scrum Team | 3 | 2026-10-21 | 2026-10-23
1.4 | US-04 Validate Contact Details (starts 1 day after US-03) | Scrum Team | 3 | 2026-10-22 | 2026-10-26
1.5 | US-05 Edit Contact (after US-03) | Scrum Team | 3 | 2026-10-26 | 2026-10-28
1.6 | US-06 Delete Contact (starts 1 day after US-05) | Scrum Team | 2 | 2026-10-27 | 2026-10-28
1.7 | US-07 Search and Filter Contacts (after US-06) | Scrum Team | 2 | 2026-10-29 | 2026-10-30
1.8 | US-08 Import Contacts (after US-05) | Scrum Team | 3 | 2026-10-29 | 2026-11-02
1.9 | US-09 Handle Import Errors (starts 2 days after US-08) | Scrum Team | 2 | 2026-11-02 | 2026-11-03
1.10 | US-10 Export Contacts (after US-08) | Scrum Team | 2 | 2026-11-03 | 2026-11-04
1.11 | US-11 Contact Module Performance testing (after US-09) | Alex (QA), Mark | 2 | 2026-11-04 | 2026-11-05
1.12 | Regression testing, Sprint review & demo (after US-11) | Scrum Team | 1 | 2026-11-06 | 2026-11-06
M1 | ◆ Milestone: Contact Management module complete | Sarah (PO) | 0 | 2026-11-06 | 2026-11-06
2.0 | Phase 2: Sales Opportunity Tracking (Epic EP-02) | Scrum Team | 10 | 2026-11-09 | 2026-11-20
M2 | ◆ Milestone: Sales Opportunity Tracking live | Sarah (PO) | 0 | 2026-11-20 | 2026-11-20
3.0 | Phase 3: Reporting and Analytics (Epic EP-03) | Scrum Team | 30 | 2026-11-23 | 2027-01-01
M3 | ◆ Milestone: Analytics dashboard launch | Sarah (PO) | 0 | 2027-01-01 | 2027-01-01
4.0 | Phase 4: Integration and Automation (Epic EP-04) | Scrum Team | 20 | 2027-01-04 | 2027-01-29
M4 | ◆ Milestone: Outlook integration & automated reminders live | Sarah (PO) | 0 | 2027-01-29 | 2027-01-29
5.0 | Phase 5: Project Closure – handover & lessons learned | David (SM), Sarah (PO) | 1 | 2027-02-01 | 2027-02-01
M5 | ◆ Milestone: Project complete | Emily Johnson, Michael Lee | 0 | 2027-02-01 | 2027-02-01
Legend:
Phase
User Story
Task (US-01 List Customer Contacts)
Milestone
Weekend (no work planned)
Assumptions:
• Durations are in working days (Mon–Fri). 1 sprint = 2 weeks = 10 working days. Each day column is one calendar day.
• Dependencies are written in brackets after each item and are built into the Start date formulas (WORKDAY).
• Public holidays (e.g. NZ Labour Day, Christmas/New Year) are not included – estimates are fictitious for this exercise.
Formulas:
Start = [Start, row above]
Start = WORKDAY([End, row above],1)
End = IF([Duration]=0,[Start],WORKDAY([Start],[Duration]-1))
Duration = NETWORKDAYS([Start],[End])

## Traceability Matrix
Feature | Req ID | Requirements | User Story IDs | Task IDs | Test IDs | Test Execution notes
Contact Management | REQ-01 | Enable sales representatives to list, view, add, edit, and delete customer contacts. Contact details must include customer name, company name, email, phone, additional details. | EP-01 (Epic) US-01, US-02, US-03, US-04, US-05, US-06, US-07 | TASK-01 to TASK-07 (US-01) Other stories: tasks defined at sprint planning | EP-01-01 US-01-01, US-01-02, US-01-03, US-01-04 US-02-01, US-02-02, US-02-03 US-03-01, US-03-02, US-03-03 US-04-01, US-04-02, US-04-03 US-05-01, US-05-02, US-05-03, US-05-04 US-06-01, US-06-02, US-06-03, US-06-04 US-07-01, US-07-02, US-07-03 | Not yet executed. Planned for Sprint 1–2 testing; US-01 tests run with TASK-06.
| REQ-02 | Allow users to import and export contact lists. | EP-01 (Epic) US-08, US-09, US-10 | Tasks defined at Sprint 2 planning | EP-01-02 US-08-01, US-08-02, US-08-03 US-09-01, US-09-02, US-09-03 US-10-01, US-10-02, US-10-03 | Not yet executed. Planned for Sprint 2 testing.
Sales Opportunity Tracking | REQ-03 | Implement functionality for users to create and update sales opportunities. | EP-02 (Epic) | Tasks defined at Sprint 3 planning | EP-02-01 | Not yet executed. Epic to be split into user stories before Sprint 3.
| REQ-04 | Provide a visual sales pipeline to track opportunities through different stages of the sales cycle. | EP-02 (Epic) | Tasks defined at Sprint 3 planning | EP-02-02 | Not yet executed. Epic to be split into user stories before Sprint 3.
Reporting and Analytics | REQ-05 | Generate reports on sales performance and customer interactions. | EP-03 (Epic) | Tasks defined at Sprint 4 planning | EP-03-02 | Not yet executed. Epic to be split into user stories before Sprint 4.
| REQ-06 | Provide dashboard analytics to visualize sales data. | EP-03 (Epic) | Tasks defined at Sprint 4 planning | EP-03-01 | Not yet executed. Epic to be split into user stories before Sprint 4.
Integration and Automation | REQ-07 | Integrate the CRM with email and calendar systems. | EP-04 (Epic) | Tasks defined at Sprint 7 planning | EP-04-01 | Not yet executed. Epic to be split into user stories before Sprint 7.
| REQ-08 | Automate reminders and follow-up tasks for sales representatives. | EP-04 (Epic) | Tasks defined at Sprint 7 planning | EP-04-02 | Not yet executed. Epic to be split into user stories before Sprint 7.
System Performance | NFR-01 | The system should be able to handle at least 500 concurrent users without any degradation in performance. | US-11 (applies to all features) | Performance testing tasks (US-11) | US-11-01 | Not yet executed. Load test in Sprint 2; repeat at end of each phase.
| NFR-02 | Page load times for any CRM feature must not exceed 3 seconds under normal network conditions. | US-11 (applies to all features) | Performance testing tasks (US-11) | US-11-02 | Not yet executed. Page load test in Sprint 2; repeat at end of each phase.
Security & Privacy | NFR-03 | Role-based access: users can only edit and delete records they are allowed to. Sales Representatives can delete only contacts and opportunities they own; Sales Managers can delete any record and view team-wide reports. | Applies to all features; delete rules apply to US-06 Delete Contact | Defined at sprint planning | To be written: role permission tests (rep vs manager) | Not yet executed. Permission tests planned from Sprint 1 and repeated each phase.
| NFR-04 | Privacy: customer personal information must be handled in line with the NZ Privacy Act 2020. Data is encrypted in transit and at rest, access is limited to authorised users, and a contact's details can be exported or removed on request. | Applies to all features (US-01 to US-11, EP-02 to EP-04) | Defined at sprint planning | To be written: privacy & security review checklist | Not yet executed. Privacy review planned before each phase goes live.
| NFR-05 | Audit trail: the system records who created, changed or deleted each contact and opportunity, and when. Audit records are kept for at least 2 years. | US-02 View Contact Details, US-05 Edit Contact (partial) | Defined at sprint planning | US-02-02, US-05-03 (partial); full audit tests to be written | Not yet executed. Partly tested in Sprint 1–2 with US-02 and US-05.
Notes: each acceptance criterion is one test case (direct mapping). Test IDs match the acceptance criteria IDs on the EPICS and User Stories tabs. ID format used across the workbook: REQ-xx (functional requirement), NFR-xx (non-functional requirement), EP-xx (epic), US-xx (user story), US-xx-yy (acceptance criterion / test case), TASK-xx (task).

## Risk Log
Risk ID | Risk description | Likelihood (1–3) | Impact (1–3) | Score | Rating | Mitigation | Owner | Status
R-01 | No buffer at the end of Sprint 2: the 11 Contact Management stories only fit in 20 days if they run in parallel. Any delay pushes Phases 2–4 out. | 3 | 2 | 6 | High | Deliver Must stories first; move Should stories to a later sprint if needed; track the sprint burndown daily. | Sarah (PO) | Open
R-02 | NZ public holidays and the Christmas/New Year break fall inside the plan but are not in the schedule, so the real end date will be later. | 3 | 2 | 6 | High | Add holidays to the WORKDAY calendar; agree a revised end date with the Project Sponsor. | David (SM) | Open
R-03 | Outlook email and calendar integration is more complex than estimated (access permissions, sync conflicts). | 2 | 3 | 6 | High | Run a technical spike in Sprint 6, before Phase 4 starts; confirm Microsoft 365 access early. | Mark (Backend) | Open
R-04 | Poor quality data in existing spreadsheets causes failed imports and duplicate contacts. | 2 | 2 | 4 | Medium | Import template, preview and error report (US-08, US-09); data clean-up with the sales team before go-live. | Tom (BA) | Open
R-05 | Low user adoption: Sales Representatives keep using spreadsheets instead of the CRM. | 2 | 3 | 6 | High | Involve reps in sprint reviews; training at the end of each phase; managers report only from CRM data. | Michael Lee | Open
R-06 | Breach of customer personal information. | 1 | 3 | 3 | Medium | Apply NFR-03 (role-based access) and NFR-04 (privacy); security review before each go-live. | Sarah (PO) | Open
Scoring: Score = Likelihood × Impact (1 = low, 3 = high). Rating: 6–9 High, 3–5 Medium, 1–2 Low. Blue numbers are inputs; Score and Rating are formulas.